OGUN STATE GOVERNMENT 
STANDARD BIDDING DOCUMENT
For the 

Procurement of 

Small Works

SEPTEMBER  2022
Notice to Users

1.
This Standard Bidding Document (SBD) has been prepared by the Ogun State Bureau of Public Procurement for the Procurement of Small Works and Related Services under State  Competitive Bidding (SCB) when financed by the Ogun State Government  Budget and to enable a Procuring Entity to select the lowest evaluated tender. 

2.
This SBD is in accordance with the Ogun State Public Procurement (Amendment) Law, 2021. The SBD when properly completed will provide all the information that a Tenderer needs in order to prepare and submit a Tender. This should provide a sound basis on which the Procuring Entity can fairly, transparently and accurately carry out a Tender evaluation process on the Tenders submitted by the Tenderers.

3.
For small, lower value works usually no pre-qualification process takes place before the Tender Document is issued. This document may be used for the Open Tendering method and for the Selective Tendering method (“Shopping”), whereby Tenders are invited from a list of pre-selected Tenderers. 

4.
This SBD is for lump sum type Contracts priced against an activity schedule, listing the main activities.  A Breakdown of Lump Sum Prices showing rates and prices for all items of the Works described in the Schedule of Works, including the delivery of materials to the Site is provided separately to giveprovided separately to provide































































































 a basis for processing progress payments to the Contractor  
Lump sum contracts are used for buildings, rehabilitation and other forms of construction where the Works are well defined and are unlikely to change in quantity or specification, and where encountering difficult or unforeseen site conditions (for example, hidden foundation problems) is unlikely.  
5.
The following guidelines apply for the Procuring Entity when using this SBD:

(a)
check the relevance of the provisions of the SBD against the requirements of the specific Works to be procured;  

(b)
tailor the document to the circumstances of the particular Project. The Procuring Entity should only introduce such adjustments in the Sections of the SBD which are specifically designed for this purpose: Section 2: the Special Instructions to Tenderers (SIT); Section 4: the Special Conditions of Contract (SCC); Section 6: Schedule of Works, including Specifications, and Section 7: Drawings. Those details not filled by the Procuring Entity are the responsibility of the Tenderer;

(c)
but never change the Instructions to Tenderers;

(d)
provide the specific information needed in the italicized notes inside brackets and boxes. These notes should also specify where the Tenderer should provide information. Footnotes and boxes solely prepared for the use of the Procuring Entity are not part of the final SBD to be issued and should be removed from the final version; 

(e)
retain the other notes and boxes which specify that they are guidance to the Tenderers.
(f)
indicate the name of the project, the contract number, the name of the Procuring Entity and the date of issue on the cover of the document;

6.
The Standard Bidding Document for the Procurement of Works has the following contents: 

IFT
Invitation for Tender (IFT): This is a repeat of the IFT which was published in the media and on the website of the Procuring Entity announcing the Tender and providing the essential information to prospective Tenderers to invite them to participate. It is reprinted here for reference purposes only

Section 1
Instructions to Tenderers (ITT): The ITT are standard instructions which guide the Tenderers how to prepare their tenders. Standard instructions mean that they cannot be modified by the Procuring Entity. The ITT are based on the Procurement Law and the Regulations for Goods and Works, from which the procedures for tender submission, opening, evaluation and Contract award have been derived. They clarify the general evaluation criteria for the selection of the lowest evaluated responsive tenderer and describe the basic qualifications of the Tenderer needed for contract execution. This Section cannot be changed under any circumstances.

Section 2
Special Instructions to Tenderers (SIT). In this Section the Procuring Entity supplements or adapts the relevant clauses of the ITT to the specific tender information or project requirements where needed (name of the Procuring Entity, tender submission date, specific evaluation criteria, amount of tender security (if applicable), tender validity period, alternative tenders permitted or not, fixed price contract or contract subject to price adjustment, works completion date, level of performance security and advance payment guarantee (if required) to be provided at contract signature, etc). Modifications to the Instructions to Tenderers cannot change the Law or the Regulations.

Section 3
General Conditions of Contract (GCC). The GCC define the conditions of contract for Works in Nigeria and are also based on the Procurement Law. Like the ITT, the GCC cannot be modified or adapted by the Procuring Entity except through the Special Conditions of Contract.

Section 4
Special Conditions of Contract (SCC). The SCC supplement or adapt the relevant clauses of the GCC to the specific requirements of the contract (in particular with respect to the starting date, description of the Works, insurance requirements, percentage of advance payment, payment schedule, price adjustment formula, subcontracting provisions, relationship with the supervising engineer, percentage of retention money and/or performance guarantee (security), liquidated damages, bonus and penalty provisions, arbitration rules, etc.).

Section 5
Standard Tender and Contract Forms. This Section provides the standard format for the Tender Submission Sheet, (Form W-1), Tenderer Information Sheet (Form W-2) and Tender Security (Form W-3), if required, to be submitted by the Tenderer.
This Section also contains the form of the Notification of Award (Form W-4) and the Contract Agreement (Form W-5) which, when completed, incorporates any corrections or modifications to the accepted Tender relating to amendments permitted by the Instructions to Tenderers, the General Conditions of Contract (GCC), and the Special Conditions of Contract (SCC).

The forms for Performance Security (Form W-6) and Advance Payment Security (Form W-7) (when required) are to be completed by the successful Tenderer after Contract award and these forms must be submitted by the successful Tenderer as a condition of contract signature. 

Section 6
Schedule of Works including Specifications: This Section provides the items and estimated quantities of Works and Related Services to be performed, as well as the detailed Technical Specifications that describe the Works to be procured and must be carefully prepared by a Procuring Entity for each object of procurement.
Section 7
Drawings: This Section contains any Drawings that supplement the Schedule of Works including Specifications for the Works and Related Services to be procured.
OGUN STATE GOVERNMENT
	[enter here the name of the procuring entity]




STANDARD TENDER DOCUMENT
FOR THE PROCUREMENT OF SMALL WORKS

	[enter here the nature of the works and related services to be procured]




Name of Procuring Entity

Invitation for Tender No:

Issued on: 

Tender Package No:
Table of Contents

1Invitation for Tenders


2Section 1:
Instructions to Tenderers


2A.
General


21.
Scope of Tender


22.
Source of Funds


23.
Corrupt Fraudulent Collusive or Coercive Practices


44.
Eligible Tenderers


55.
Site Visit


5B.
Tender Document


56.
Sections of the Tender Document


57.
Clarification of the  Tender Document


68.
Amendment of the Tender Document:


6C.
Tender Preparation


69.
Only one Tender


610.
Preparation Costs of the Tender


611.
Tender Language


612.
Contents of the Tender


713.
Alternative Tenders


714.
Prices and Currency of Tenders


715.
Validity and Security of Tenders


716.
Tender Format and Signing


8D.
Tender Submission


817.
Tender Sealing and Marking


818.
Tender Submission Deadline


819.
Late Tenders


920.
Tender Modification, Substitution or Withdrawal


9E.
Tender Opening and Evaluation


921.
Tender Opening


22.
Confiden-tiality
9
1023.
Tender Clarification


1024.
Tenderer Contacting the Employer


1025.
Tender: Responsi-veness


26.
Minor Deviations
10
1127.
Evaluation and Comparison of Tenders


1128.
No Negotiations


1129.
Employer’s Right to Accept or Reject any or all Tenders


11F.
Contract Award


1130.
Award Criteria


1131.
Notification of Award


1232.
Performance Security


1233.
Contract Signing


1234.
Tenderer’s Right to Complain


12Section 2. Special Instructions To Tenderers


12A.
General


14B.
Tender Document


14C.
Preparation of Tenders


15D.
Submission of Tenders


15E.
Tender Opening and Evaluation


16F.
Award of Contract


16Section 3.
General Conditions of Contract


161.
Definitions


162.
Interpretation & Documents forming the Contract


173.
Corrupt, Fraudulent, Collusive or Coercive Practices


184.
Governing Language and Law


185.
Engineer’s Decision


186.
Delegation


197.
Communications and Notices


198.
Sub- Contracting & Assigning


199.
Contractor’s Personnel


1910.
Welfare of Labourers and wages


1911.
Safety, Security and Protection of the Environment


1912.
Access to the Site


1913.
Documents, Information.


1914.
Property


2015.
Insurance


2016.
Possession of the Site


2017.
Commencement of Works


2018.
Completion of Works


2019.
Programme of Works


2120.
Early Warning


2121.
Compens- ation Events


2122.
Non-Scheduled Items of Works


.23.
Schedule of Works
.................................................................................................21
2224.
Payment Certificates


2225.
Payments and Currency


2226.
Retention


2227.
Liquidated Damages


2328.
Performance Security


2329.
Cost of Repairs


2330.
Completion


2331.
Correction of Defects


2332.
Taking Over


2333.
Final Account


2334.
Termination


2435.
Payment upon Termination


2436.
Release from Performance


2437.
Settlement of Disputes


26Section 4.
Special Conditions of Contract


29Section 5.
Tender and Contract Forms


30Tender Submission Sheet (Form W-1)


31Tenderer Information Sheet (Form W-2)


33Bank Guarantee for Tender Security (Form W-3)


34Notification of Award (Form W-4)


35Contract Agreement (Form W-5)


36Bank Guarantee for Performance Security (Form W-6)


37Bank Guarantee for Advance Payment (Form W-7)


38Section 6.
Schedule of Works including Technical Specifications


39Section 7.
Drawings




[ Note: The Invitation for Tenders that follows on the next page is the standard format as it should appear on the website. The procuring entity should ensure that a hard copy of the Invitation for Tenders as actually published is included in the issued Tender Document.]

Invitation for Tenders

	Section 1:
Instructions to Tenderers

	A.
General

	1. Scope of Tender
	1.1 The Employer, as indicated in the Special Instructions To Tenderers (SIT) issues this Tender Document for the procurement of Works and Related Services incidental thereto as specified in the SIT and as detailed in Section 6: Bill of Quantities. The name of the Tender and the number and identification of its constituent lot(s) are stated in the SIT.

	2. 
	1.2 The successful Tenderer will be required to complete the Works within the Time for Completion stated in the Special Conditions of Contract (SCC).

	3. 
	1.3 Throughout this Tender Document:

(a) the term “in writing” means communicated in written form with proof of receipt;

(b) if the context so requires, singular means plural and vice versa; and

(c) “day” means calendar day.

	4. Source of Funds
	2.1 The Employer has been allocated public funds as indicated in the SIT and intends to apply a portion of the funds to eligible payments under the Contract for which this Tender Document is issued

	5. 
	2.2 For the purpose of this provision, “public funds” means any monetary resources appropriated to procuring entities under Government budget, or revenues generated by statutory bodies and corporations, or aid grants and credits put at the disposal of procuring entities by the development partners through the Government.

	6. 
	2.3 Payments by the development partner, if so indicated in the SIT, will be made only at the request of the Government and upon approval by the development partner in accordance with the applicable Loan/Credit/Grant Agreement, and will be subject in all respects to the terms and conditions of that Agreement.

	7. Corrupt Fraudulent Collusive, Coercive or Obstructive Practices
	3.1 The Government requires that Employers, as well as Tenderers and Contractors shall observe the highest standard of ethics during the implementation of procurement proceedings and the execution of Contracts under public funds

	
	3.2 In pursuance of this requirement, the Employer shall 

(a) exclude the Tenderer from participation in the procurement proceeding concerned or reject a proposal for award; and

(b) declare a Tenderer ineligible, either indefinitely or for a stated period of time, from participation in procurement proceedings under public funds;

(c) have the right to require that a provision be included in bidding documents, requiring bidders, suppliers and contractors to permit the relevant authorities  to inspect their accounts and records and other documents relating to the bid submission and contract performance and to have them audited by auditors if it, at any time, determines that the Tenderer has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a Contract under public funds.

	
	3.3 Should any corrupt, fraudulent, collusive or coercive practice of any kind come to the knowledge of the Employer, it shall, in the first place, allow the Tenderer/Contractor to provide an explanation and shall, take actions as above only when a satisfactory explanation is not received.

	
	3.4 The Government defines, for the purposes of this provision, the terms set forth below as follows:

(a) “corrupt practice” means offering, giving, or promising to give, directly or indirectly, to any officer or employee of a Procuring Entity or other governmental/private authority or individual a gratuity in any form, an employment or any other thing or service of value, as an inducement with respect to an act or decision of, or method followed by, a Procuring Entity in connection with the procurement proceeding; 

(b) “fraudulent practice” means a misrepresentation or omission of facts in order to influence a procurement proceeding or the execution of a Contract to the detriment of the Employer; 

(c) “collusive practice” means a scheme or arrangement among two and more Tenderers with or without the knowledge of the Employer (prior to or after Tender submission) designed to establish Tender prices at artificial, non-competitive levels and to deprive the Employer of the benefits of free, open and genuine competition; and 

(d) “coercive practice” means harming or threatening to harm, directly or indirectly, persons or their property to influence the procurement proceedings, or affect the execution of a Contract.
(e) “obstructive practice” which means
i. deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede relevant authorities’  investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or

ii. acts intended to materially impede the exercise of the relevant authorities’ inspection and audit rights provided for under par. 3.2 (c) above.

	
	3.5 The Tenderer shall be aware of the provisions on fraud and corruption stated in GCC Clause 3 and GCC Sub-Clause 34.2(d).

	
	3.6 The Government requires that the Employer’s personnel have an equal obligation not to solicit, ask for and/or use coercive methods to obtain personal benefits in connection with the said proceedings.

	8. Eligible Tenderers
	4.1 [Tenderers of the categories specified in the SIT are eligible to participate in the Tender.]

	9. 
	4.2 A Government-owned enterprise in Nigeria may also participate in the Tender if it is legally and financially autonomous, it operates under commercial law, and it is not a dependent agency of the Employer.

	
	4.3 For Restricted Tendering method, Tenderers shall provide satisfactory information to the Employer of their capability and adequacy of resources to carry out the Contract effectively as defined in the Tender Document.

	
	4.4 When there are no enlisted contractors of the Employer to enable the use of the Restricted Tendering method, and the Employer shall invite Tenders using the Open Tendering Method (State Competitive Tendering), the Tenderers shall provide satisfactory information to the Employer of their capability and adequacy of resources to carry out the Contract effectively and shall meet the following minimum qualifying criteria:

(a) average annual volume of construction turnover as specified in the SIT during the period specified in the SIT;

(b) experience as prime Contractor or subcontractor in the construction of at least the number of completed Contracts stated in the SIT of a nature and complexity similar to the proposed work over the period stated in the SIT; and

(c) liquid assets/ availability of funds and/or credit facilities from its Banker’s to successfully complete the Contract, as specified in the SIT.

	10. Site Visit
	5.1 The Tenderer, at the Tenderer’s own responsibility and risk, is encouraged to visit and examine the Site and obtain all information that may be necessary for preparing the Tender and entering into a Contract for performance of the Works. The costs of visiting the Site shall be at the Tenderer’s own expense.

	B.
Tender Document

	11. Sections of the Tender Document 
	6.1 The sections comprising the Tender Document are listed below and should be read in conjunction with any Amendment issued in accordance with ITT Clause 9:

· Section 1:
Instructions to Tenderers

· Section 2:
Special Instructions To Tenderers
· Section 3:
General Conditions of Contract

· Section 4:
Special Conditions of Contract
· Section 5:
Tender and Contract Forms

· Section 6:
Schedule of Works & Technical Specifications

· Section 7:
Drawings


	12. Clarification of the Tender Document 
	7.1 A prospective Tenderer requiring any clarification of the Tender Document shall contact the Employer in writing at the Employer’s address indicated in the SIT. The Employer will respond in writing to any request for clarification received no later than seven (7) calendar days prior to the deadline for submission of Tenders.

	
	7.2 The Employer shall forward copies of its response to all those who have purchased the Tender Document, including a description of the enquiry but without identifying its source.

	
	7.3 Should the Employer deem it necessary to amend the Tender Document as a result of a clarification, it shall do so following the procedure under ITT Clause 8 and ITT Sub-Clause 18.3

	13. Amendment of the Tender Document: 
	8.1 At any time prior to the deadline for submission of Tenders, the Employer for any reason, on its own initiative or in response to a clarification request in writing from a Tenderer, having purchased the Tender Document, may amend the Tender Document by issuing an amendment.

	5. 
	8.2 Any amendment issued shall become an integral part of the Tender Document and shall be communicated in writing to all those who have purchased the Tender Document.

	C.
Tender Preparation

	14. Only one Tender
	9.1 A Tenderer shall submit only one (1) Tender for each lot. A Tenderer who submits or participates in more than one (1) Tender will cause all the Tenders with that Tenderers participation to be rejected.

	15. Preparation Costs of the Tender 
	10.1 The Tenderer shall bear all costs associated with the preparation and submission of its Tender, and the Employer shall not be responsible or liable for those costs, regardless of the conduct or outcome of the Tendering process.

	16. Tender Language
	11.1 The Tender, as well as all correspondence and documents relating to the Tender shall be written in the English language.

	17. Contents of the Tender 
	12.1 For the Restricted Tendering method using enlisted Contractors, the Tender prepared by the Tenderer shall comprise the following:

(a) the Tender Submission Sheet  (Form W-1);

(b) the completed Schedule of Works including Technical Specifications (Section 6);

(c) the Tender Security in accordance with ITT Cub-Clause 15.2;

(d) the completed Tenderer Information Sheet (Form W-2);

(e) any other documents as specified in the SIT.

	
	12.2 For the Open Tendering method (State Competitive Bidding), the Tender prepared by the Tenderer shall comprise the following:

(a) the Tender Submission Sheet (Form W-1);

(b) the completed Schedule of Works  (section 6);

(c) the Tender Security in accordance with ITT Sub-Clause 15.2;

(d) the documentary evidence in accordance with ITT Sub-Clause 4.4 establishing Tenderer’s eligibility to Tender, including the completed Tender Information Sheet (Form W-2); and

(e) any other documents as specified in the SIT.

	18. Alternative Tenders
	13.1 Alternative tenders shall not be considered.

	19. Prices and Currency of Tenders 
	14.1 All prices shall be quoted in Naira.

	
	14.2 The Tender price shall take into account the cost of materials, transportation, labour, taxes, levies, overheads and profit. The Tender price shall be fixed for the duration of performance of the Contract and shall not be subject to any adjustment on any account. The Tender price shall be applicable for the whole works described in the Drawings, Specifications and Schedule of Works.

	
	14.3 The Tenderer shall fill in a lump sum price for each component of the Works identified in the Schedule of Works.  In addition, the Tenderer shall provide a breakdown of the lump sum price(s) showing rates and prices for all items of the Works described in the Schedule of Works.

	
	14.4 The price to be quoted in the Tender Submission Sheet shall be the total price of the Tender, excluding any discounts offered. In the case of a discrepancy between the Tender Price quoted in figures and words the Tender Price quoted in words shall prevail.

	20. Validity and Security of Tenders
	15.1 Tenders shall remain valid for the period specified in the SIT after the date of Tender submission prescribed by the Employer, pursuant to ITT Clause 18. A Tender valid for a shorter period shall be rejected by the Employer as non-responsive.

15.2 The Tender Security shall at the Tenderer’s option, be either in the form of a bank draft, pay order or an unconditional bank guarantee (Form W-3) issued by a commercial Bank of Nigeria.

	6. 
	15.3 In exceptional circumstances, prior to the expiration of the Tender validity period, the Employer may solicit the Tenderers consent to an extension of the period of validity of their Tenders. The request and responses shall be made in writing. The Tender Security provided under ITT Sub-Clause 15.2 shall be suitably extended promptly.

	21. Tender Format and Signing
	16.1 The Tenderer shall prepare one (1) original of the documents comprising the Tender as described in ITT Clause 12 and clearly mark it “ORIGINAL.”  In addition, the Tenderer shall prepare the number of copies of the Tender, as specified in the SIT and clearly mark each of them “COPY.”  In the event of any discrepancy between the original and the copies, the original shall prevail.

	
	16.2 The original and each copy of the Tender shall be typed or written in indelible ink and shall be signed by the person duly authorized to sign on behalf of the Tenderer. All pages of the original and of each copy of the Tender, except for un-amended printed literature, shall be numbered sequentially and signed or initialled by the person signing the Tender

	
	16.3 Any interlineations, erasures, or overwriting shall be valid only if they are signed or initialled by the person(s) signing the Tender.

	D.
Tender Submission

	22. Tender Sealing and Marking
	17.1 The Tenderer shall enclose the original in one (1) envelope and all the copies of the Tender in another envelope, duly marking the envelopes as “ORIGINAL” and “COPY.” These two (2) envelopes shall then be enclosed in one (1) single outer envelope.

	
	17.2 The inner and outer envelopes shall: 
(a) bear the name and address of the Tenderer;

(b) be addressed to the Employer at the address specified in the SIT;

(c) bear the name of the Tender and the Tender Number as specified in the SIT, and;

(d) bear a statement “DO NOT TO OPEN BEFORE.......” the time and date for Tender opening as specified in the SIT.

	
	17.3 If all envelopes are not sealed and marked as required by ITT Sub-Clause 17.2, the Employer will assume no responsibility for the misplacement or premature opening of the Tender

	23. Tender Submission Deadline
	18.1 Tenders must be received by the Employer at the address specified in  the SIT not later than the date and time specified in the SIT.

	
	18.2 Tenders may be hand delivered, posted by registered mail or sent by courier. The Employer shall, on request, provide the Tenderer with a receipt showing the date and time when its Tender was received.

	
	18.3 The Employer may, at its discretion, extend the deadline for the submission of Tenders by amending the Tender Document in accordance with ITT Clause 8, in which case all rights and obligations of the Employer and Tenderers previously subject to the deadline shall thereafter be subject to the new deadline as extended.

	24. Late Tenders 
	19.1 Any Tender received by the Employer after the deadline for submission of Tenders in accordance with ITT Clause 18 shall be declared late, will be rejected, and returned unopened to the Tenderer.

	25. Tender Modification, Substitution or Withdrawal
	20.1 A Tenderer may modify, substitute or withdraw its Tender after it has been submitted by sending a written notice before the deadline for submission of Tenders. 

	
	20.2 Each Tenderer’s modification, substitution or withdrawal notice shall be prepared, sealed, marked, and delivered in accordance with ITT Clauses 16, 17, and 18 with the outer and inner envelopes additionally marked “MODIFICATION”, “SUBSTITUTION” or “WITHDRAWAL” as appropriate.

	E.
Tender Opening and Evaluation

	26. Tender Opening
	21.1 The Employer shall open the Tenders in public, including modifications or substitutions made pursuant to ITT Clause 20, at the time, on the date and only at the one place specified in the SIT. Tenders for which an acceptable notice of withdrawal has been submitted pursuant to ITT Clause 20 shall not be opened. Tenderers or their authorised representatives shall be allowed to attend and witness the opening of Tenders, and shall sign a register evidencing their attendance. 

	
	21.2 The name of the Tenderer, Tender modifications, substitutions or withdrawals, total amount of each Tender, number of corrections, discounts, and the presence or absence of requisite Tender Security, and such other details as the Employer, at its discretion, may consider appropriate, shall be read out aloud and recorded. All pages of the original Tender, except for un-amended printed literature, will be initialled by a minimum of three (3) members of the Employer’s Tender Opening Committee.

	
	21.3 Minutes of the Tender opening shall be made by the Employer and furnished to any Tenderer upon receipt of a written request. The minutes shall include, as a minimum, the name of the Tenderer and whether there has been a withdrawal, substitution or modification; the Tender Price including any discounts and the presence or absence of a Tender Security, if one was required.

	
	21.4 Tenders not opened and read out at the Tender opening shall not be considered, irrespective of the circumstances, and shall be returned unopened to the Tenderer.

	
	21.5 No Tender shall be rejected at the Tender opening, except for late Tenders, which shall be returned unopened to the Tenderer pursuant to ITT Clause 19

	27. Confidentiality
	22.1 After the opening of Tenders, information relating to the examination, clarification, and evaluation of Tenders and recommendations for award shall not be disclosed to Tenderers or other persons not officially concerned with the evaluation process until after the award of the Contract is announced.

	28. Tender Clarification
	23.1 The Employer may ask Tenderers for clarification of their Tenders in order to facilitate the examination and evaluation of Tenders. The request for clarification and the response shall be in writing, and any changes in the prices or substance of the Tender shall not be sought, offered or permitted, except to confirm the correction of arithmetical errors discovered by the Employer in the evaluation of the Tenders, in accordance with ITT Clause 27.

	29. Tenderer Contacting the Employer
	24.1 Following the opening of Tenders and until the Contract is signed no Tenderer shall make any unsolicited communication to the Employer or try in any way to influence the Employer’s examination and evaluation of Tenders.

	
	24.2 Any effort by a Tenderer to influence the Employer in its decisions on the examination, evaluation, comparison and post-qualification of the Tenders or Contract award may result in the rejection of its Tender.

	
	24.3 Notwithstanding ITT Sub Clause 24.1, from the time of Tender opening to the time of Contract award, if any Tenderer wishes to contact the Employer on any matter related to the tendering process, it should do so in writing.

	30. Tender:   Responsiveness
	25.1 The Employer’s determination of a Tender’s responsiveness is to be based on the contents of the Tender itself without recourse to extrinsic evidence.

	
	25.2 A substantially responsive Tender is one that conforms in all respects to the requirements of the Tender Document without material deviation, reservation or omission. A material deviation, reservation or omission is one that:

(a) affects in any substantial way the scope, quality, or performance of the Works specified in the Contract; or 

(b) limits in any substantial way, or is inconsistent with the Tender Document, the Employer’s rights or the Tenderer’s obligations under the Contract; or

(c) if rectified would unfairly affect the competitive position of other Tenderers presenting substantially responsive Tenders.

	
	25.3 If a Tender is not substantially responsive to the Tender Document it shall be rejected by the Employer and shall not subsequently be made responsive by the Tenderer by correction of the material deviation, reservation or omission. 

	
	25.4 There shall be no requirement as to the minimum number of responsive Tenders.

	31. Minor Deviations


	26.1 The Employer may regard a Tender as responsive even if it contains minor deviations that do not materially alter or depart from the characteristics, terms, conditions and other requirement set forth in the Tender Document or if it contains errors or oversights that are capable of being corrected without affecting the substance of the Tender.

	27. Evaluation and Comparison of Tenders
	27.1 The Employer shall evaluate and compare only those Tenders determined to be substantially responsive to the requirements of the Tender Document. Substantially responsive tenders are those which fulfil the requirements of ITT Clauses 4 and 12.

	
	27.2 The evaluation will take into account the corrected Tender Price and discounts (if any).
27.3 The Employer will check substantially responsive Tenders for any arithmetical errors including in the computation of the breakdown of lump sum price(s). Where there is a discrepancy between the amounts in figures and words, the amount in words will govern. If a Tenderer refuses to accept the correction, its Tender shall be rejected. The Employer shall correct arithmetical errors on the following basis :
(a)  if there is a discrepancy between the unit price and the line item total, the unit price shall prevail and the total price shall be corrected, unless in the opinion of the Employer there is an obvious misplacement of the decimal point in the unit price, in which case the total price, as quoted, shall govern and the unit price shall be corrected ; and

(b) where there is a discrepancy between the amounts in figures and words, the amount in words will govern. 

	28. No Negotiations
	28.1 No Negotiations shall be held with the lowest or any other Tenderer. A Tenderer shall not be required, as a condition for award, to undertake responsibilities not stipulated in the Tender document, to change its price or otherwise modify its Tender.

	29. Employer’s Right to Accept or Reject any or all Tenders
	29.1 The Employer reserves the right to accept any Tender, to annul the Tender proceedings, or to reject any or all Tenders, at any time prior to Contract award, without thereby incurring any liability to Tenderers, or any obligation to inform Tenderers of the grounds for the Employer’s actions.

	F.
Contract Award

	30. Award Criteria
	30.1 The Employer shall award the Contract to the Tenderer whose offer is substantially responsive to the Tender Document and that has been determined to be the lowest evaluated Tender, provided that the Tenderer is determined to be qualified to perform the Contract satisfactorily.

	31. Notification of Award
	31.1 Prior to the expiration of the period of Tender validity, the Employer shall notify the successful Tenderer, in writing that its Tender has been accepted. 

	
	31.2 Until a formal contract is prepared and executed, the Notification of Award shall constitute a binding Contract.

	32. Performance Security
	32.1 Within fourteen (14) days of the receipt of the Notification of Award from the Employer, the successful Tenderer shall furnish the Performance Security, if required, in the amount specified in the SIT using for that purpose the Performance Security Form (Form W-6) furnished in Section 5: Tender and Contract Forms.

	33. Contract Signing
34. Information to Tenderers.

35.Tenderer’s Right to Complain
	33.1  At the same time as the employer issues the notification of award, the employer shall send the contract agreement and all documents forming the contract to the successful tenderer.
33.2 Within twenty-one (21) days of receipt of the contract agreement, the successful tenderer shall sign, date and return it to the employer.
33.3 Failure of the successful Tenderer to submit the Performance Security, pursuant to ITT Sub-Clause 32.1, or sign the Contract, pursuant to ITT Sub-Clause 33.2, shall constitute sufficient grounds for the annulment of the award and forfeiture of the Tender Security. In that event, the Employer may award the Contract to the next lowest evaluated responsive Tenderer at their quoted price (corrected for arithmetical errors), who is assessed by the Employer to be qualified to perform the Contract satisfactorily.

33.4 Immediately upon receipt of the signed Contract Agreement and Performance Security from the successful Tenderer, the Employer shall discharge and return the successful Tenderer’s Performance Security.

	35. 
	34.1 Upon the successful Tenderer’s furnishing of the Performance Security pursuant to ITT Clause 32, and signing of the Contract pursuant to ITT Clause 33, the Employer shall also notify all other Tenderers that their Tenders have been unsuccessful.
34.2 The Employer shall promptly respond in writing to any unsuccessful Tenderer who, after notification in accordance with ITT Sub-Clause 34.1, requests in writing for the Employer to communicate the grounds on which its Tender was not selected.

	
	35.1 Any Tenderer has the right to complain if it has suffered or may suffer loss or damage in accordance with the provisions of the PPA (Amendment) Law, 2021.


	
	

	
	


	Section 2. Special Instructions To Tenderers

	Instructions for completing the Special Instructions To Tenderers are provided, as needed, in the notes in italics mentioned for the relevant ITT Clauses

	ITT

Clause
	Amendment of, and Supplements to, Clauses in the Instructions to Tenderers

	A.
General

	ITT 1.1
	The Employer is [state name of Employer] represented by [state name of representative].

[the Employer is the unit or subdivision of the Procuring Entity which will issue the Notification of Award and sign the Contract Agreement with the successful Tenderer. Frequently the Employer is represented by a Chief Engineer, Superintending Engineer, Executive Engineer, project director or other assigned person. ]

	
	The Name of the Tender is 

The number and identification of lots comprising the Tender lot are:

[if there is more than one lot, individual lots are to be identified in conformity with Section 6: Schedule of Works].

	ITT 2.1
	The source of public funds is [state source OGSG,  FGN, or other source of funds]



	ITT 2.3
	The name of the Development Partner is [state name of Development Partner or “None” as applicable].



	ITT 4.1
	The Tendering method is :

	ITT 4.4
	[The following qualification criteria are  applicable for the contract:] 

	
	(a)
Annual Turnover:
The required average annual turnover shall be greater than Naira [insert amount] over the last [insert number] years:

As a guide, the required average annual turn over should be at least equal to the estimated annual cash flow for the Contract. (It is preferable to be more), and the period should be about 5 years minimum.
Example 1:

Estimated Contract Value:

Naira 10 million
Contract period:


3 months

Monthly Cash flow: 30m N:3 = 

Naira 3.3 million
Estimated Annual Cash Flow:
12 x 3.3 m = Naira 39.6 M
[Required Average annual turnover would be Naira 40 million, using a multiplier of 1.0 as a minimum and rounding the figure, however it is not recommended to exceed a multiplier of 1.5].

Example 2:

Estimated Contract Value:

Naira 5 million

Contract Period:


2 months

Monthly Cash flow: 5m N:2 =

Naira 2.5 million

Estimated Annual Cash Flow: 
12 x 2.5 million = Naira  30 million

 [Required Average annual turnover would be Naira 30 million, using a multiplier of 1.0 as a minimum, however it is not recommended to exceed a multiplier of 1.5].



	

	(b)
Specific Experience:
Participation as contractor, management contractor, or subcontractor, in at least _________ (___) contracts within the last ________( ) years , each with a value of at least ____________ (___), that have been successfully and substantially completed and that are similar to the proposed Works. 
[the minimum number will depend upon the size and type of construction work, and the Employer should make its own judgement based upon its experience in the sector and construction industry. For small contracts, it could be (2) similar work during the past 3 or 5 years. And the value to be at least 80% of the contract value].

	
	(c)
Liquid Assets:

The minimum amount of liquid assets and/or credit facilities net of other contractual commitments of the Tenderer shall be [insert amount].

[The liquid asset should not be less than 30% of the contract value.]
d.  General Experience
Experience under contracts in the role of contractor, subcontractor, or management contractor for at least the last________ [____] years prior to the applications submission deadline, and with activity in at least nine (9) months in each year.  
e.  Personnel

The Bidder must demonstrate that it will have the personnel for the key positions that meet the following requirements:

No.

Position

Total Work  Experience (years)

Specific Works Experience
       (years)

1

2

3

4

5

The Bidder shall provide details of the proposed personnel and their experience records in the relevant Forms (Form W – 2)
f.           Equipment

The Bidder must demonstrate that it will have access to the key Contractor’s equipment listed hereafter:

No.

Equipment Type and Characteristics

Minimum Number required

1

2

3

4

5

The Bidder shall provide further details of proposed items of equipment using the relevant Form in Section IV.



	f.      Equipment

The Bidder must demonstrate that it will have access to the key Contractor’s equipment listed hereafter:

No.

Equipment Type and Characteristics

Minimum Number required

1

2

3

4

5

The Bidder shall provide further details of proposed items of equipment using the relevant Form (Form W – 2)
B.
Tender Document

	ITT 7.1
	For clarification of Tenders purposes only, the Employer’s address is:

Attention: 

Address: 

Telephone: 

Facsimile number:

Electronic mail address:

	C.
Preparation of Tenders

	ITT 12.1(e)
	Additional documents to be submitted by Tenderers are:

[list the additional documents required]

	ITT 12.2 (e)
	Additional documents to be submitted by Tenderers are:

[list the additional documents required].

	ITT 15.1
	The Tender validity period shall be [    ] days.

[normally 45 to 60 days for Works of such a simple nature]

	ITT 15.2
	A Tender Security in the amount of Naira [insert amount] will be required, 
OR

A Tender Security will not be required:

[delete whichever is not required]

.  The Tender Security amount should be expressed as a fixed amount (around 2% and in no case exceeding 5% of the estimated contract value) for each lot. OR

A Tender Security shall not be required (this may be considered in the case of small works)]

	ITT 16.1
	In addition to the original of the Tender, [    ] copies shall be submitted.

[usually only two copies are needed, ask for more only if they are essential].

	D.
Submission of Tenders

	ITT 17.2
	The inner and outer envelopes shall bear the following additional identification marks:

[indicate any markings that are required on inner and outer envelopes

	ITT 17.2
	For Tender submission purposes only, the Employer’s address is:

Attention:

Address: 

The deadline for the submission of Tenders is:

Time & Date

	E.
Tender Opening and Evaluation

	ITT 21.1
	The Tender opening shall take place at:

Address:

Time & Date:

[Tenders shall be opened immediately only in one place, but in no case more than one hour, after the deadline for submission of Tenders.]

	F.
Award of Contract

	ITT 32.1
	The amount of Performance Security shall be [   ] percent of the Contract Price.

[It should not be less than five (5) percent and not exceed ten (10) percent of the Contract Price. If, in addition, Retention Money is applied, the percentages of the Performance Security and the Retention Money combined should not exceed fifteen (15) percent . Higher percentages will require a more costly financing arrangement between the Tenderer and its Bank or financial provider, and will only increase the cost of the Tenders]

[The Performance Security shall be issued by a reputable bank or financial institution selected by the Tenderer and acceptable to the Employer. A Tenderer may request the Employer in advance if a particular issuing entity of a security is acceptable. If an issuing entity is foreign but the security is otherwise in conformity with the requirements in the Tender Document, the Employer shall not reject the security.]


	ITT 34.2
	The name and address of the office where complaints to the Procuring Entity are to be submitted under S. 58 of the Law is :


	Section 3.
General Conditions of Contract

	1. Definitions
	1.1 The following words and expressions shall have the meaning hereby assigned to them. Boldface type is used to identify the defined terms:

(a) Completion Certificate means the Certificate issued by the Engineer as evidence that the Contractor has executed the Works in all respects as per drawing, specifications, and Conditions of Contract.

(b) The Completion Date is the date of completion of the Works as certified by the Engineer, in accordance with GCC Clause 18.

(c) Contract means the Agreement entered into between the Employer and the Contractor to execute, complete and maintain the Works.

(d) Contractor means the person or corporate body whose Tender to carry out the Works has been accepted by the Employer and is named as such in the SCC.

(e) Contract Price means the price payable to the Contractor as specified in the Contract Agreement.

(f) The Contractor’s Tender is the completed Tender Document including the priced offer submitted by the Contractor to the Employer.

(g) Days means calendar days.

(h) A Defect is any part of the Works not completed in accordance with the Contract.

(i) The Employer is the party named in the SCC who employs the Contractor to carry out the Works.

(j) The Engineer is the person named in the SCC, who is responsible for supervising the execution of the works and administering the Contract.

(k) The Intended Completion Date is the date specified in the SCC on which the Contractor shall complete the Works and may be revised if extension of time or an acceleration order is issued by the Engineer.

(l) The Site is the area defined as such in the SCC.

(m) The Works are what the Contract requires the Contractor to construct, install, and hand over to the Employer, as defined in the SCC.

	2. Interpretation & Documents forming the Contract
	2.1 In interpreting the GCC, singular also means plural, male also means female or neuter, and the other way around. Headings in the GCC shall not be deemed part thereof or be taken into consideration in the interpretation of the Contract. Words have their normal meaning under the language of the Contract unless specifically defined. 

	
	2.2 The following documents forming the Contract shall be interpreted in the following order of priority:

(a) the signed Contract Agreement.

(b) the letter of Notification of Award.

(c) the completed Tender Submission Sheet as submitted by the Tenderer.

              (d)  the priced Schedule of Works as submitted by the Tenderer.

             (e)  the Technical Specifications 

             (f)  the Drawings,

             (g)  any other document listed in the SCC as forming part of the Contract.

	3. Corrupt, Fraudulent, Collusive, Coercive or Obstructive Practices
	3.1 The Government requires that Employers, as well as Contractors shall observe the highest standard of ethics during the implementation of procurement proceedings and the execution of Contracts under public funds.

	
	3.2 In pursuance of this requirement, the Employer shall

(a) exclude the Contractor from participation in the procurement proceedings concerned or reject a proposal for award; and

(b) declare a Contractor ineligible, either indefinitely or for a stated period of time, from participation in procurement proceedings under public fund;

(c) if it at any time determines that the Contractor has engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a Contract under public fund.



	
	3.3 Should any corrupt, fraudulent, collusive or coercive practice of any kind referred to in GCC Sub-Clause 3.4 come to the knowledge of the Employer, it shall, in the first place, allow the Contractor to provide an explanation and shall, take actions as stated in GCC Sub-Clause 3.2 only when a satisfactory explanation is not received. Such exclusion and the reasons thereof, shall be recorded in the record of the procurement proceedings and promptly communicated to the Contractor concerned. Any communications between the Contractor and the Employer related to matters of alleged corrupt, fraudulent, collusive or coercive practices shall be in writing.

	
	3.4 The Government defines, for the purposes of this provision, the terms set forth below as follows:

(a) “corrupt practice” means offering, giving, or promising to give, directly or indirectly, to any officer or employee of a Procuring Entity or other governmental/private authority or individual a gratuity in any form, an employment or any other thing or service of value, as an inducement with respect to an act or decision of, or method followed by, a Procuring Entity in connection with the procurement proceeding;

(b) “fraudulent practice” means a misrepresentation or omission of facts in order to influence a procurement proceedings or the execution of a Contract to the detriment of the Employer;

(c) “collusive practice” means a scheme or arrangement among two or more Tenderers with or without the knowledge of the Employer (prior to or after proposal submission) designed to establish Tender prices at artificial, non-competitive levels and to deprive the Employer of the benefits of free, open and genuine competition; and

(d) “coercive practice” means harming or threatening to harm, directly or indirectly, persons or their property to influence the procurement proceedings, or affect the execution of a Contract.

(e) obstructive practice which means

i. deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede relevant authorities’  investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or
ii. acts intended to materially impede the exercise of the relevant authorities’ inspection and audit rights provided for under par. 3.2 (c) above.

	
	3.5 The Government requires that the Client’s personnel have an equal obligation not to solicit, ask for and/or use coercive methods to obtain personal benefits in connection with the said proceedings.



	4. Governing Language and Law
	4.1 The Contract as well as all correspondence and documents relating to the Contract exchanged by the Contractor and the Employer, shall be written in English. 

	
	4.2 The Contract shall be governed by and interpreted in accordance with the laws of the Federal Republic of Nigeria / Arbitration Laws of Ogun State ….. CHECK  WITH MOJ

	5. Engineer’s Decision
	5.1 Except where otherwise specifically stated in the SCC, the Engineer will decide Contractual matters between the Employer and the Contractor in the role as representative of the Employer.

	6. Delegation
	6.1 The Engineer may delegate any of his duties and responsibilities to his representative, after notifying the Contractor, and may cancel any delegation, without retroactivity, after notifying the Contractor.

	7. Communications and Notices
	7.1 Communications between Parties pursuant to the Contract shall be in writing to the address specified in the SCC. A notice shall be effective when delivered or on the notice’s effective date, whichever is later.

	8. Sub- Contracting & Assigning 
	8.1 The Contractor shall not be permitted to subcontract any part of the Works, nor shall the Contractor be allowed to assign the Contract in whole or in part.

	9. Contractor’s Personnel
	9.1 The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the SCC, to carry out the functions stated in the Schedule, or other personnel approved by the Engineer.

	
	9.2 If the Engineer asks the Contractor to remove a person who is a member of the Contractor’s staff or work force from the Site, he shall state the reasons, and the Contractor shall ensure that the person leaves the Site within three (3) days and has no further connection with the work in the Contract.

	10. Welfare of Labourers and wages
	10.1 The Contractor shall provide proper accommodation to his labourers and arrange proper water supply, conservancy and sanitation arrangements at the site in accordance with relevant regulations, rules and orders of the government.

	
	10.2 The Contractor shall pay reasonable wages to his labourers, and pay them in time. [In the event of delay in payment the Employer may effect payments to the labourers and recover the cost from the Contractor.]

	11. Safety, Security and Protection of the Environment
	11.1 The Contractor shall throughout the execution and completion of the Works and the remedying of any defects therein :

(a) have full regard for the safety of all persons entitled to be upon the Site and keep the Site and the Works in an orderly state;

(b) provide and maintain at the Contractors own cost all lights, guards, fencing, warning signs and watching for the protection of the Works or for the safety on-site; and 

(c)  take all reasonable steps to protect the environment on and off the Site and to avoid damage or nuisance to persons or to property of the public or others resulting from pollution, noise or other causes arising as a consequence of the Contractors methods of operation.

	12. Access to the Site 
	12.1 The Contractor shall allow the Engineer and any person authorised by the Engineer access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out.

	13. Documents, Information.
	13.1 The Contractor shall furnish to the Engineer all information, schedules, calculations and supporting documentation that may be requested of it.

	14. Property
	14.1 All materials on the Site, Plant, Equipment, Temporary Works and Works shall be deemed to be the property of the Employer if the Contract is terminated because of the Contractor’s default.

	15. Insurance
	15.1 The Contractor shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts and deductibles stated in the SCC for the following events which are due to the Contractor’s risks:

(a) loss of or damage to the Works, Plant and Materials

(b) loss of or damage to Equipment;

(c) loss of or damage to property (except the Works, Plant, Materials and Equipment) in connection with the Contract; and 

(d) personal injury or death.

	
	15.2 The Contractor shall deliver policies and certificates of insurance to the Engineer, for the Engineer’s approval, before the Start Date.

	
	15.3 If the Contractor does not provide any of the policies and certificates required, the Employer may effect the insurance which the Contractor should have provided and recover the premiums the Employer has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due.

	
	15.4 Alterations to the terms of insurance shall not be made without the approval of the Engineer.

	
	15.5 Both parties shall comply with conditions of the insurance policies.

	16. Possession of the Site
	16.1 The Employer shall give possession of the Site, or parts of the Site, to the Contractor on the date(s) specified in the SCC.

	17. Commencement of Works
	17.1 The Contractor may commence execution of the Works on the Start Date, or other such date as specified in the SCC, and shall carry out the Works in an expeditious manner.

	
	17.2 If the Contractor fails to commence the works within the above stated period, the Employer may, at his sole discretion, terminate the Contract and forfeit the Performance Security, if any.

	18. Completion of Works
	18.1 The Contractor shall complete the Works within the number of days stated in the SCC from the date of commencing the Works on the Site.

	19. Programme of Works
	19.1 Within the time stated in the SCC, the Contractor shall submit to the Engineer for approval a Programme showing the general methods, arrangements, order and timing for all the activities of the Works.

	
	19.2 The Contractor shall submit to the Engineer for approval an updated Programme at intervals no longer than the period stated in the SCC. 

	
	19.3 If the Contractor does not submit an up-dated programme at the intervals stated in the SCC, the Engineer may withhold an amount as stated in the SCC from the next payment certificate and continue to withhold this amount until the next due payment after the date on which the overdue Programme has been submitted.

	20. Early Warning
	20.1 The Contractor shall notify the Engineer in writing at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, result in increase to the Contract Price or delay in the execution of the Works.  

	21. Compens- ation Events
	21.1 The following shall be Compensation Events:

(a)
the Employer does not give access to the Site or part of the Site by the Site Possession Date stated in the SCC; and

(b)
if the payment is delayed pursuant to Clause 25.1.

	
	21.2 If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date shall be extended, as appropriate, by the Engineer. 

	22. Non-Scheduled Items of Works
	22.1 The Contractor shall be paid for non-scheduled items of works only when the Engineer approves such works and at the rates and in the manner stated in the SCC.

	23. Schedule of Works 

	22.2 The priced Schedule of Works shall contain the priced activities for the Works to be performed by the Contractor. The Schedule of Works is used to monitor and control the performance of activities on which basis the Contractor will be paid. If payment for Materials on Site shall be made separately, the Contractor shall show delivery of Materials to the Site separately on the Schedule of Works.

	
	23.1 The priced Schedule of Works shall contain the priced activities for the Works to be performed by the Contractor. The Schedule of Works is used to monitor and control the performance of activities on which basis the Contractor will be paid. If payment for Materials on Site shall be made separately, the Contractor shall show delivery of Materials to the Site separately on the Schedule of Works.

	
	23.2 The Schedule of Works shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion.  Prices in the Schedule of Works shall not be altered when the Contractor makes such changes to the Activity Schedule.
23.3 The Contractor shall be entirely responsible for all taxes, duties, license fees, and other such levies. The Engineer shall adjust the Contract Price if taxes, duties, and other levies are changed between the date 28 days before the submission of bids for the Contract and the date of the last Completion Certificate. 

	24. Payment Certificates
	24.1 The Contractor shall submit to the Engineer monthly statements of the estimated value of the work executed less the cumulative amount certified previously.

	
	24.2 The Engineer shall check the Contractor’s monthly statement and certify the amount to be paid to the Contractor.

	
	24.3 The value of work executed shall be determined by the Engineer.

	
	24.4 The value of work executed shall comprise the value of the completed activities in the Schedule of Works.

	
	24.5 The value of work executed shall include the valuation of Compensation Events. 

	
	24.6 The Engineer may exclude any item certified in previous certificates or reduce the proportion of any item previously certified in any certificate in the light of later information.

	25. Payments and Currency
	25.1 The Employer shall pay the Contractor the amounts certified by the Engineer within twenty-eight (28) days of the date of each certificate. All payments shall be made in Naira.

	
	25.2 The Employer shall make Advance Payment to the Contractor of the amounts and by the dates stated in the SCC against provision by the Contractor of an unconditional Bank Guarantee, (Form W-7).

	
	25.3 The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for the execution of the Contract. The Contractor shall demonstrate that the advance payment has been used in this way by supplying copies of invoices or other documents to the Employer.

	
	25.4 The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, claims or any amount payable due to failure to complete

	26. Retention
	26.1 The Employer shall retain from each payment due to the Contractor the proportion stated in the SCC until the completion of the whole of the Works.

	
	26.2 On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor, the remaining half shall be repaid when the Defects Liability Period has passed and the Engineer has certified that all Defects notified by the Engineer to the Contractor before the end of this period have been corrected.

	27. Liquidated Damages
	27.1 The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the SCC for each day that the Completion Date is later than the Intended Completion date for the works or for any part thereof.

	28. Performance Security
	28.1 If so specified in the SCC, a Performance Security shall be provided to the Employer in the amount stated in the SCC using the  form in the Contract Forms (Form W-5). The Performance Security shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion.

	29. Cost of Repairs
	29.1 Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions

	30. Completion
	30.1 The Contractor shall request the Engineer to issue a Certificate of Completion of the Works, and the Engineer will do so upon deciding that the work is completed.

	31. Correction of Defects
	31.1 The Engineer shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the SCC. The Defects Liability Period shall be extended for as long as the Defects remain to be corrected.

	
	31.2 If the Contractor has not corrected a Defect within the time specified in the Engineer’s notice, the Engineer will assess the cost of having the Defect corrected, and the Contractor will pay this amount.

	32. Taking Over
	32.1 The Employer shall take over the Site and the Works within seven (7) days of the Engineer issuing a Certificate of Completion.

	33. Final Account
	33.1 The Contractor shall supply the Engineer a detailed account of the total amount that the Contractor considers payable under the Contract. The Engineer shall certify any final payment that is due to the Contractor within twenty-one (21) days of receiving the Contractor’s account if it is correct and complete.

	
	33.2 The Employer shall effect payment of the final account within twenty-eight (28) days from the date of certification by the Engineer.

	34. Termination
	34.1 The Employer or the Contractor by giving twenty-eight (28) days written notice of default to the other party, may terminate the Contract in whole or in part if the other party causes a fundamental breach of Contract.

	35. 
	34.2 Fundamental breaches of the Contract shall include, but shall not be limited to, the following: 

(a) the Contractor stops work for more than twenty-eight (28) days when no stoppage of work is shown on the current Programme and the stoppage has not been authorised by the Engineer;

(b) the Engineer gives notice that failure to correct a particular defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Engineer;

	
	(c) the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of Liquidated Damages can be paid;

(d) the Contractor, in the judgment of the Employer, has engaged in corrupt or fraudulent practices, as defined in GCC Clause 3, in competing for or in executing the Contract; or  
(e) a payment certified by the Engineer is not paid to the Contractor by the Employer within seventy (70) days of the date of the Engineer’s certificate. 

	
	34.3 The Employer and the Contractor may at any time terminate the Contract by giving notice to the other party if either of the parties becomes bankrupt or otherwise insolvent. In such event, termination will be without compensation to any party provided that such termination will not prejudice or affect any right of action or remedy that has accrued or will accrue to the other party.

	
	34.4 Notwithstanding the above, the Employer may terminate the Contract for convenience. 

	
	34.5 If the Contract is terminated, the Contractor is to stop work immediately, make the Site safe and secure and hand over the Site to the Employer as soon as reasonably possible.

	36. Payment upon Termination
	35.1 If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Engineer shall issue a certificate for the value of the work done and Plant and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the SCC. Additional Liquidated Damages shall not apply.  If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer.

	
	35.2 If the Contract is terminated for the Employer’s convenience or because of a fundamental breach of Contract by the Employer, the Contractor shall be entitled to payments for completed works and the materials that have been brought to the site for the purpose of the works, but not used as certified by the Engineer after adjusting any payments received by the Contractor.

	37. Release from Performance
	36.1 If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the Employer or the Contractor, the Engineer shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible, after receiving this certificate. The Contractor shall be paid for all works carried out before stoppage of work and any work carried out afterwards to which a commitment was made.

	38. Settlement of Disputes
	37.1 The Employer and the Contractor shall use their best efforts to settle amicably all disputes arising out of or in connection with this Contract or its interpretation.

	
	37.2 Any dispute between the parties to the Contract that may not be settled amicably will be referred to Arbitration at the initiative of either of the parties.

	
	37.3 The arbitration shall be conducted in accordance with the [Arbitration Act (Act No  of…..) of Nigeria] as at present in force and in the place shown in the SCC.CHECK WITH MOJ


Section 4.
Special Conditions of Contract
	Instructions for completing the Special Conditions of Contract are provided, as needed, in the notes in italics mentioned for the relevant GCC Clauses.

	Clause

Ref
	Amendments of, and Supplements to, Clauses in the General Conditions of Contract 

	GCC 1.1(d)
	The Contractor is [name, address and name of authorised representative].

	GCC 1.1(i)
	The Employer is [name, address and name of authorised representative].

	GCC 1.1(j)
	The Engineer is [name and address of the Engineer].

	GCC 1.1(l)
	The Site is located at [enter location of Site].

	GC   C 1.1(m)
	The Works are [enter the name of the Works]

	GCC 2.2(h)
	The additional documents forming part of this Contract are:

[if there are no additional documents state “No additional documents”.]

	GCC 5.1
	The Engineer shall obtain specific approval of the Employer before taking any of the following actions:

	GCC 7.1
	The addresses for Communications shall be:

For the Employer:

 [insert name, address and contact details]
For the Contractor:
[insert name, address and contact details].

	GCC 9.1
	The Key Personnel of the Contractor are:

	GCC  15.1
	For insurance purposes the type of cover required shall be:

	
	Type of Cover
	Amount of Cover
	Exclusions

	
	The Works, Materials and Plant
	The Contract Sum 
	

	
	Contractor’s Equipment
	Full replacement cost
	

	
	
	
	

	
	Third Party injury to persons and damage to property
	
	

	
	Workers
	
	

	
	The Works, Materials and Plant: [insert maximum value at risk, which should usually be less than the contract]
	
	

	GCC 16.1
	Possession of the site shall be within [     ] days from the date of signing of the Contract.

	GCC 17.1
	Commencement of work shall be within [     ] days from the date of handing over possession of the Site.

	GCC 18.1
	Completion of works shall be within [     ] days from the date of commencing the works on the site.

	GCC 19.1

& 19.2
	The Contractor shall submit the first Programme of Works [….] days after signing the Contract, and shall update the Programme every [……..] weeks during the period of the Contract.

	GCC 22.1
	[ Enter here the agreed rates for non-scheduled items of work if known, if not known then make the statement “The rates for non-scheduled items of works shall be determined by the Engineer”.

	GCC 25.2
	An advance payment of 15 % of the Contract Price will be made to the Contractor within (14) days of Contract signing date.

[usually, an advance payment is made for mobilisation, if admissible to the Employer considering the nature of the works. The recommended maximum advance is 15% of the Contract Price against an unconditional bank guarantee (Form W-7). The procuring entity should amend this clause as required for the particular procurement.]

	GCC 26.1
	The Retention shall be [insert percentage]% of the Contract Price.

(The retention should not exceed 5% if a performance guarantee is also required)

	GCC 27.1
	The liquidated damages for the whole of the Works are [percentage of the final Contract Price] per day.

The maximum amount of liquidated damages for the whole of the Works is [insert number] percent of the final Contract Price.

[usually, liquidated damages are set between 0.05 of one percent and 0.10 of one percent per day (or half of one percent per week of delay) and the total amount is not to exceed 10 percent of the Contract Price.]

	GCC 28.1
	 A performance Security is required in the amount of [insert amount or percentage of contract price]” 
Or
A performance Security is not required. 

	GCC 31.1
	The Defects Liability Period shall be [         ] days.

	GCC 35.1
	The percentage to apply to the value of the work not completed, representing the Employer’s additional cost for completing the Works, is [percent]

	GCC 37.3
	 The place for Arbitration shall be : 


Section 5.
Tender and Contract Forms

	Form
	Title

	



Tender Forms

	W-1
	Tender Submission Sheet

	W-2
	Tenderer Information Sheet

	W-3
	Bank Guarantee for Tender Security

	



Contract Forms

	W-4
	Notification of Award

	W-5
	Contract Agreement

	W-6
	Bank Guarantee for Performance Security

	W-7
	Bank Guarantee for Advance Payment 


Forms W1-W3 comprise part of the Tender Format and should be completed as stated in ITT Clause 12.

Forms W4-W7 comprise part of the Contract as stated in GCC Clause 2.

Tender Submission Sheet (Form W-1)

Invitation for Tender No:




Date:

Tender Package No:

To:

[Name and address of Employer]

We, the undersigned, offer to execute in conformity with the Conditions of Contract and associated Contract Documents, the following Works and Related Services, viz:

	[state here a brief description of the Works and Related Services]




The total Price of our Tender is:

	Naira:

[state amount in figures]
	[state amount in words]


Our Tender shall be valid for the period stated in the Special Instructions To Tenderers and it shall remain binding upon us and may be accepted at any time before the expiration of that period. A Tender Security in the amount stated in the Special Instructions To Tenderers is attached in the form of a [bank draft, pay order, bank guarantee] valid for a period of 28 days beyond the Tender validity date. [include this sentence only if a Tender Security is required].

If our Tender is accepted, we commit to obtaining a Performance Security in the amount stated in the Special Instructions To Tenderers and valid for a period of 28 days beyond the issue of the Certificate of Completion of Works.

We declare that we, and any subcontractors or Contractors for any part of the Contract have not been declared ineligible by the Ogun State Government on charges of engaging in corrupt, fraudulent, collusive or coercive practices. Furthermore, we are aware of ITT Clause 3 concerning this and pledge no not to indulge in such practices in competing for or in executing the Contract.  

We are not participating as Tenderers in more than one Tender in this tendering process. We understand that your written Letter of Award shall constitute the acceptance of our Tender and shall become a binding Contract between us, until a formal Contract is prepared and executed. 

We understand that you are not bound to accept the lowest evaluated Tender or any other Tender that you may receive.

	
	Signed



	
	In the capacity of:



	
	Duly authorised to sign the Tender on behalf of the Tenderer

	
	Date




Tenderer Information Sheet (Form W-2)

All Tenderers shall include the following information and documents with their Tenders:

	Notes on Tenderer Information Sheet

The information to be filled in by Tenderers in the following pages will be used for purposes of verification of eligibility and qualification of the Tenderer as provided for in relevant Clauses of the Instructions to Tenderers. 

The Tenderer, if prequalified earlier, should fill in updated information only.

 Additional pages may be attached as necessary.

This information will not be incorporated in the Contract.




Tender No:

Invitation for Tender No:

	1. Name and value of Works performed in the last 5 years.(Specific Experience)


	Year
	Name of Works
	Value of Works
	Name of Employer

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	

	2. Name and value of Works performed .(General  Experience)


	Year
	Name of Works
	Value of Works
	Name of Employer

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	

	3. The Tenderer should list the Equipment deemed essential for carrying out the Works.



	Type of Equipment
	No. Available
	Owned / Leased (and from whom)

	
	
	

	
	
	

	
	
	

	4. Evidence of financial capability to perform this Contract. The Tenderer should list cash in hand, lines of credit, and attach supporting documentary evidence

	1

	2

	3

	4

	5

	5. Schedule of Key Personnel



	Sl

No
	Position
	Name
	Qualification
	Experience

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	6. Average Annual Turnover


	Year
	Amount
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	


_______________________________

[Signature and Seal of the Tenderer]

Name: _______________________

Address:______________________

_____________________________

_____________________________

_____________________________

Date: _________________

Bank Guarantee for Tender Security (Form W-3)

[this is the format for the Tender Security to be issued by a commercial Bank

 of Nigeria in accordance with ITT Clause 15]
	Invitation for Tender No:


	Date:

	Tender Package No:


	

	To:

[Name and address of Employer]


	


TENDER GUARANTEE No: 
We have been informed that [name of Tenderer] (hereinafter called “the Tenderer”) intends to submit to you its Tender dated [date of Tender] (hereinafter called “the Tender”) for the execution of the Works of [description of works] under the above Invitation for Tenders (hereinafter called “the IFT”).

Furthermore, we understand that, according to your conditions tenders must be supported by a Tender Guarantee.

At the request of the Tenderer, we [name of bank] hereby irrevocably undertake to pay you, without cavil or argument, any sum or sums not exceeding in total an amount of Naira [insert amount in figures and words] upon receipt by us of your first written demand accompanied by a written statement that the Tenderer is in breach of its obligation(s) under the Tender conditions, because the Tenderer:

(a) has withdrawn its Tender during the period of Tender validity specified by the Tenderer in the Form of Tender; or

(b) does not accept the correction of errors in accordance with the Instructions to Tenderers ITT; or

(c) having been notified of the acceptance of the Tender by the Employer during the period of Tender validity, (i) fails or refuses to furnish the performance security in accordance with the ITT, or (ii) fails or refuses to execute the Contract Form,

This guarantee will expire 

(a) if the Tenderer is the successful Tenderer, upon our receipt of a copy of the Performance Security and a copy of the Contract signed by the Tenderer as issued by you; or

(b) if the Tenderer is not the successful Tenderer, twenty eight days after the expiration of the Tenderer’s Tender validity period, being [date of expiration of the Tender].
Consequently, we must receive at the above-mentioned office any demand for payment under this guarantee on or before that date.

	Signature
	Signature


Notification of Award (Form W-4) TO BE DELETED
	Contract No:


	Date:

	To:

[name and address of Contractor]


	


This is to notify you that your Tender dated [insert date] for the execution of the Works for [name of project / Contract] for the Contract Price of Naira [amount in figures and in words], as corrected and modified in accordance with the Instructions to Tenderers is hereby accepted by [name of the Employer]. 
You are requested to proceed with the execution of the Works on the basis that this Notification of Award shall constitute the formation of a Contract, which shall become binding upon you furnishing a Performance Security within fourteen (14) days, in accordance with ITT Clause 32, and the signing the Contract Agreement within twenty-one (21) days, in accordance with ITT Clause 33.

We attach the Contract Agreement and Special Conditions of Contract for your perusal and signature.

	
	Signed

Duly authorised to sign for and on behalf of

[name of Procuring Entity]

	
	Date:


Contract Agreement (Form W-5) TO BE DELETED
THIS AGREEMENT, made the [day] of [month] [year] between [name and address of Employer] (hereinafter called “the Employer”) of the one part and [name and address of Contractor] (hereinafter called “the Contractor”) of the other part.

WHEREAS, the Employer invited Tenders for certain Works, viz, [brief description of the Works] and has accepted a Tender by the Contractor for the execution of those works in the sum of Naira [insert amount in figures and words], hereinafter called “the Contract Price.
NOW THIS AGREEMENT WITNESSETH as follows:

1. In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the General Conditions of Contract hereinafter referred to. 

2. The documents forming the Contract shall be interpreted in the following order of priority:

(a) The signed Contract Agreement;

(b) The letter of Notification of Award;

(c) The completed Tender Submission Sheet as submitted by the Tenderer;

(d) The priced Schedule of Works  as completed by the Tenderer;

(e) The Special Conditions of Contract;

(f) The General Conditions of Contract;

(g) Technical Specification

(h) The Drawings; and

(i) Any other document listed in the SCC as forming part of the Contract.
3.
In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and to remedy any defects therein in conformity in all respects with the provisions of the Contract.

4.
The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the Parties thereto have caused this Agreement to be executed in accordance with the laws of Nigeria on the day month and year first before written.

	
	For the Employer
	For the Contractor



	Signature


	
	

	Print Name


	
	

	Title


	
	

	In the presence of (Name)


	
	

	Address


	
	


Bank Guarantee for Performance Security (Form W-6)

[this is the format for the Performance Security to be issued by a commercial bank

 of Nigeria in accordance with ITT Clause 32]
	Contract No:


	Date:

	
	

	To:

[Name and address of Employer]


	


PERFORMANCE GUARANTEE No: 
We have been informed that [name of Contractor] (hereinafter called “the Contractor”) has undertaken, pursuant to Contract No [reference number of Contract] dated [date of Contract] (hereinafter called “the Contract”), the execution of works [description of works] under the Contract.

Furthermore, we understand that, according to your conditions, Contracts must be supported by a performance guarantee.

At the request of the Contractor, we [name of bank] hereby irrevocably undertake to pay you, without cavil or argument, any sum or sums not exceeding in total an amount of Naira [insert amount in figures and in words] upon receipt by us of your first written demand accompanied by a written statement that the Contractor is in breach of its obligation(s) under the Contract conditions, without your needing to prove or show grounds or reasons for your demand of the sum specified therein.

This guarantee is valid until [date of validity of guarantee], consequently, we must receive at the above-mentioned office any demand for payment under this guarantee on or before that date.

	Signature
	Signature


Bank Guarantee for Advance Payment (Form W-7)

[this is the format for the Advance Payment Guarantee to be issued by a commercial bank

 of Nigeria in accordance with SCC Clause 25.2]
	Contract No:


	Date:

	
	

	To:

[Name and address of Employer]


	


ADVANCE PAYMENT GUARANTEE No: 
We have been informed that [name of Contractor] (hereinafter called “the Contractor”) has undertaken, pursuant to Contract No [reference number of Contract] dated [date of Contract] (hereinafter called “the Contract”), the execution of works [description of works] under the Contract.

Furthermore, we understand that, according to your conditions, Advance Payments must be supported by a bank guarantee.

At the request of the Contractor, we [name of bank] hereby irrevocably undertake to pay you, without cavil or argument, any sum or sums not exceeding in total an amount of Naira [insert amount in figures and in words] upon receipt by us of your first written demand accompanied by a written statement that the Contractor is in breach of its obligation(s) under the Contract conditions, without you needing to prove or show grounds or reasons for your demand of the sum specified therein.

We further agree that no change, addition or other modification of the terms of the Contract to be performed, or of any of the Contract documents which may be made between the Employer and the Contractor, shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee is valid until [date of validity of guarantee], consequently, we must receive at the above-mentioned office any demand for payment under this guarantee on or before that date.

	Signature
	Signature


Section 6.
Schedule of Works including Technical Specifications

	Item No.
	Specification Clause Number
	Brief Description of Works
	Unit of Works
	Quantity of Works
	Unit Rate (in Naira)
	Total Amount

(in Naira)

	1
	2
	3
	4
	5
	6
	7 = 5x6

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	Total Amount in Naira
	


The objectives of the Schedule of Works including Technical Specifications are:

(a)
to provide sufficient information on the quantities of Works to be performed to enable Tenders to be prepared efficiently and accurately; and

(b)
when a Contract has been entered into, to provide a priced Schedule for use in the periodic valuation of Works executed.

In order to attain these objectives, Works should be itemized in the above schedule in sufficient detail to distinguish between the different classes of Works, or between Works of the same nature carried out in different locations or in other circumstances that may give rise to different considerations of cost.  Consistent with these requirements, the layout and content of the Schedule should be as simple and brief as possible. If required the Technical Specifications for particular items or classes of work should be specified in more detail in the form of notes attached to this Section.

Section 7.
Drawings

	Notes on Drawings

Insert here a list of Drawings.  The actual Drawings, including site plans, should be attached to this section or annexed in a separate folder. The Drawings shall be dated, numbered and show the revision number.




Section 8.
Technical Specification
