## Slide 1
OGUN STATE ECONOMIC TRANSFORMATION PROJECT
(World Bank Funded)
IMPLEMENTATION SUPPORT MISSION (ISM 8)
DEC 1 - 5, 2025
BUSINESS ENABLING ENVIRONMENT
Implementation Completion Status
Sheriff Mohammed
Project Manager

## Slide 2: Content
Project Background Overview
Sector PDO Implementation Status
Outstanding Project Activities.
Sustainability
Key Project Achievements
Progress of Project Outcomes
Close-Out Notes

## Slide 3: Project Background Overview

## Slide 4: Introduction
The sector’s primary objective is strengthening capacity and effectiveness of the Ogun State Business Environment Council and other MDAs to design and implement ease of doing business reforms in an inclusive way that would help reduce the time to start business, register property and obtain construction permit
The objective of the subsector is to strengthen the Land Administration System by institutionalizing world best practices that guarantees seamless and secure issuance of Certificate of Occupancy.
The Ogun State Investment Promotion and Facilitation Agency (Ogun Invest) mandate is to strengthen the State’s capacity to promote, attract and retain domestic and foreign private investments, to be measured by the number new service agreement signed between Investors and OgunInvest
DLI 1
DLI 2
DLI 3

## Slide 5: Sector PDO Implementation Status 100%

## Slide 6: Project (PDO) To improve the business enabling environment for private sector participation and facilitate at least 10 investment deals through the Ogun State Investment Promotion and Facilitation Agency each with a minimum of 5m USD

## Slide 7: Outstanding Project Activities.

## Slide 8
S/N | Contractor | Lot | Sites | % completion | Outstanding Activities | Estimated completion and Handover Date
Rehabilitation of e planning centers |  |  |  |  |  | 
 | Okenla B and Sons | 1 | Isheri, Sagamu and Ijebu Ode | 90 | Landscaping, Cleaning | December 15 2025
 | DC Engineering Ltd | 2 | Abeokuta Data Center 1, Abeokuta Central Planning Office 2, Abeokuta H/Q Oke Ilewo 3 and Otta | 98 | Hand-over ceremony | December 15

## Slide 9
S/N | Contractor | Lot | Sites | % completion | Outstanding Activities | 
Equipment supply, installation and commissioning of the e planning centers |  |  |  |  |  | 
1 | Hyperlink Ltd | 1 | Isheri, Sagamu and Ijebu Ode | 80% | Installation and Commissioning | 
 |  |  | Abeokuta Data Center 1, Abeokuta Central Planning Office 2, Abeokuta H/Q Oke Ilewo 3 |  |  | 
2 | First Prime Oak |  | Isheri, Sagamu and Ijebu Ode | 100% |  | 
 |  |  | Abeokuta Data Center 1, Abeokuta Central Planning Office 2, Abeokuta H/Q Oke Ilewo 3 |  |  | 
3 | Ise Ini |  | Isheri, Sagamu and Ijebu Ode | 80% | Installation and commissioning | 
 |  |  | Abeokuta Data Center 1, Abeokuta Central Planning Office 2, Abeokuta H/Q Oke Ilewo 3 |  |  | 

## Slide 10: Completion of Outstanding Project Activities-Consultancies
Enhancement of OLARMS (Ogun Land Administration and Revenue Management System) for Improved Production and Issuance of Statutory Land Title Documents in Ogun State.
– 80% complete Estimated Completion December 15 2025
Media Consultancy for OgunInvest
– 90% complete. Estimated Completion December 15 2025

## Slide 11: Sustainability Plans

## Slide 12: Sustainability Plans
Intervention/ Initiative | Exit Strategy | Sustainability Measures | Responsible Party | Remarks
Rehabilitation of 7 Zonal Town e-Planning Offices, HQ-e-Planning Office | Hand over to State Ministry of Physical Planning and Urban Development | Inclusion in annual budget; continuous ICT maintenance | Ministry of Physical Planning and Urban Development | Routine state financing required
Establishment of Technical Working Groups (TWGs) under OGBEC | 7 TWGs inaugurated and functional across key reform areas are running independently | Implementing Agencies have a budget line for each TWG | OGBEC | Routine state financing required
Equipping of OGBEC secretariat | OGBEC secretariat fully equipped and functi0nal | The secretariat already has a budget line. | OGBEC | Routine state financing required

## Slide 13: Sustainability Plans
Intervention/ Initiative | Exit Strategy | Sustainability Measures | Responsible Party | Remarks
Enhancement of OLARMS (Ogun Land Administration and Revenue Management System) for Improved Production and Issuance of Statutory Land Title Documents in Ogun State. | The buy-in of the Bureau of Lands and Survey was secured by sign-offs, and capacity building of the staff of the BLS/BIT was done by the vendor | Dedicated ICT maintenance fund; system integration. Budget considerations have been considered | Bureau of Lands & Survey Bureau of IT | 

## Slide 14: Sustainability Plans
Intervention/ Initiative | Exit Strategy | Sustainability Measures | Responsible Party | Remarks
Implementation of spatial Land Use/Land Cover (LULC) Mapping of Ogun State | The buy-in of the Bureau of Lands and Survey was secured by sign-offs, and capacity building of the staff of the BLS/BIT was done by the vendor | Dedicated ICT maintenance fund; system integration. Budget considerations have been considered | Bureau of Lands & Survey Bureau of IT | 

## Slide 15: Sustainability Plans
Intervention/ Initiative | Exit Strategy | Sustainability Measures | Responsible Party | Remarks
Institutionalization of Investment Promotion Agency (IPA) OGUNINVEST | Institutional mainstreaming | OGUNINVEST is already independent and sustainable | OGUNINVEST | 

## Slide 16: Key Project Achievements

## Slide 17: Key Project Achievements
Delivery of 15,473 CofOs
Facilitation of 53 out of 40 investment deals in Ogun State
Securing 11 out 10 investment deals, with each one worth a minimum of 5 million USD.
Piloting of e-planning through the Ministry of Physical Planning and Urban Development in 7 areas of the State.
Enhancement of OLARMS from 6 to 11 modules
Implementation of the Land Use/Land Cover in 11 areas of interest in the State.
Furnishing and equipping of the Bureau of Lands and Survey, and the Bureau of Information Technology.
Equipping and furnishing of the 7 e planning centers

## Slide 18: Progress of Project Outcomes

## Slide 19: Progress of Project Outcomes
Delivery of 15,473 CofOs, targeting 16,200 by December 2025
Facilitation of 43 investment deals in Ogun State
Securing 10 investment deals, with each one worth a minimum of 5 million USD.
Piloting of e-planning through the Ministry of Physical Planning and Urban Development in 7 areas of the State
Implementation of the Land Use/Land Cover in 11 areas of interest in the State.
Furnishing and equipping of the Bureau of Lands and Survey, and the Bureau of Information Technology.
Equipping and furnishing of the e planning centers

## Slide 20: Close-Out Notes

## Slide 21: Close-Out Notes
OGBEC has been running independent of the project and they are encouraged to keep it up
The BLS/BIT have the OLARMS enhancement and the SDI/LULC to ensure its sustainability, the buy-in by getting signatures and the capacity building of the staff of the BLS/BIT. Budgetary considerations have been made in the subsequent budgets
OgunInvest have done extremely well in line with its mandate. They are encouraged to keep it up